## Slide 1
Project Management Tools
Channing Philbrick (phlbrck2@illinois.edu)
Notes: ECE Main Slide

## Slide 2
What is the most common reason for project failure?

## Slide 3
What is the most common reason for project failure?
Bad planning!

## Slide 4
Motivation
Things take time
Some tasks depend on other tasks
Fair workload between team members
Engineering projects rely on many external factors
  Parts procurement
  Lab equipment availability
  Scheduling conflicts (midterms, classes, etc.)

## Slide 5
In this course…
We require a basic schedule only
However, we suggest using additional management tools
https://courses.engr.illinois.edu/ece445/documents/examples/ExampleDD.pdf

## Slide 6
Common Management Tools
Winging it
Stoplight charts
Risk matrices
Gantt charts
Increasing Complexity

## Slide 7
Stoplight Charts
Red: A problem exists that cannot be fixed
  Critical system design failure
  Significant delay in parts procurement
Yellow: A problem exists that can be fixed
  Schedule change
  Potential design issue
Green: Task is on track
http://clipartbarn.com/stoplight-clipart_20273/

## Slide 8
Stoplight Charts
Week | Task | Owner | Notes
2/12/18 | Receive and characterize sensors | Bert | Unexpected manufacturer delay: +4 weeks
2/12/18 | Circuit board population and testing | Ernie | Accidentally shorted power lines during testing – multiple components burnt. Can repopulate with spare parts
2/12/18 | Code debugging | Bert | No debugging necessary; magically worked the first time

## Slide 9
Risk Matrices
Assess impact of potential project failures
Minimize number of high-impact items
Base timeline and major project decisions off of matrix
(ALARP = as low as reasonably practical)
https://www.cgerisk.com/knowledgebase/Risk_matrices

## Slide 10
Risk Matrices
1
2
3
Probability
1
2
3
Severity
Capacitor out of tolerance
Sensor does not meet specification
Systems integration failure
PCB design flaw
Subsystem failure

## Slide 11
Gantt Charts
Used for developing complex timelines
Based on key inputs
  Project milestones
  Duration of task
  Dependencies on prior tasks
  Availability of resources
  Availability of personnel
Free software
  MS Projects (UIUC Web Store)
  Gantter (Google Drive plugin)

## Slide 12
Gantt Charts

## Slide 13
Gantt Charts
Milestones are fixed dates used to guide project planning
  Typically indicate major project deadlines
  Help define what needs to happen by when

## Slide 14
Gantt Charts
Duration is based on estimation
  Estimation of how long a task will take based on available knowledge
  It is important to revise estimations as information comes to light
  Accurate estimation is best, but when in doubt, air on the side of over-estimation

## Slide 15
Gantt Charts
Categories help organize tasks
  Break down tasks by subsystem or top-level category
  Denoted by brackets on timeline

## Slide 16
Gantt Charts
Dependencies define order
  Certain tasks cannot occur until other tasks have been completed
  Denoted by arrows on chart

## Slide 17
Gantt Charts
Resources may also act as dependencies
  Individual workers often cannot work on multiple tasks at once
  Equipment availability determines if a task can be worked on

## Slide 18
Lessons I’ve learned the hard way
Systems integration always takes longer than expected
Build in slip to any schedule – you’ll need it
Do your research – inaccurate time/resource estimation can ruin a project
Nothing is worse than finding out your project won’t work halfway through the semester

## Slide 19
Quick Lesson: Bad Research
Goal: Measure altitude-dependent atmospheric density
Implementation
  High-altitude balloon
  Elastic Backscatter Lidar (uses a laser)
Timeline: 6 weeks
What we missed: FAA licensing for lasers
The problem: Not enough remaining time to get a license
Effects
  Could not legally operate payload
  Had to re-scope project during Week 4

## Slide 20
The Bottom Line – Work as a team
Time and task management is useless without a functional team
Understand how your partners are doing – what is their progress?
Support your teammates emotionally and professionally
Hold yourself accountable
Communicate! If there’s a problem, address it
If you’re struggling, don’t be afraid to ask for help